## Gantchart
GANTT CHART | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE: ACADEMIC TASK MANAGEMENT SYSTEM | [6 empty] | INSTUTUTE & DEPARTMENT NAME: A.P SHAH INSTITUTE OF TECHNOLOGY [Computer Science Engineering (Data Science)]
PROJECT GUIDE: PROF. VAIBHAV YAVALKAR | [6 empty] | DATE: | [6 empty] | 11-10-2022
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PERCENTAGE OF TASK COMPLETE | PHASE ONE | [39 empty] | PHASE TWO
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Group formation and Topic finalization. Identifying the scope and objectives of the Mini Project | Riya, Veena, Sanika, Janvi | 2022-07-26 | 2022-08-03 | 2 | 100% | bar: WEEK 1 M to WEEK 2 F
1.2 | Identifying the functionalities of the Mini Project | Janvi, Veena | 2022-08-10 | 8-16-22 | 1 | 100% | bar: WEEK 3 M to WEEK 3 F
1.3 | Discussing the project topic with the help of paper prototype. | Riya, Veena, Sanika, Janvi | 2022-08-16 | 2022-08-23 | 1 | 100% | bar: WEEK 4 M to WEEK 5 F
1.4 | Designing the Graphical User Interface(GUI) | Riya, Sanika | 2022-08-23 | 2022-09-13 | 3 | 100% | bar: WEEK 5 M to WEEK 7 F
1.5 | Presentation I | Riya, Sanika, Veena, Janvi | 2022-09-19 | 2022-09-23 | 1 | 100% | bar: WEEK 8 M to WEEK 8 F
2 | Project Design and Implementation
2.1 | Database Design | Janvi,Veena | 2022-09-20 | 2022-09-27 | 1 | 100% | bar: WEEK 9 M to WEEK 9 F
2.2 | Database Connectivity of all modules | Riya, Janvi | 9-29-22 | 2022-05-10 | 1 | 100% | bar: WEEK 10 M to WEEK 11 F
2.3 | Integration of all modules and Report Writing | Riya, Janvi, Sanika, Veena | 2022-09-10 | 10-16-22 | 1 | 100%
2.4 | Presentation II | Riya, Sanika, Veena, Janvi | 2022-10-17 | 2022-10-21 | 2 | 100% | bar: WEEK 11 M to WEEK 13 F